## ProjectFlow - Changemarks
Changemarks Report - Electrical
Project Name: |  |  | PIP-0023-22
Workflow Started: |  |  | 03/10/2022 1:53 PM
Report Generated: |  |  | 04/04/2022 09:26 AM
| Grouping | Cycle |  | Ref # | Complete? | Status | Department | Snapshot | File | Markup Name | Changemark Subject | Changemark Details | Markup Date | Updated By | Applicant Response
| Main Workflow | 1 |  | 47 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | Quantity | Only 2 new lights. | 03/29/2022 6:58 AM | Dan Hazel | MFIA: Revised street lighting plans will only have one new fixture to meet the required light levels indicated in comment #56.
|  |  |  | 48 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | Fixture | Please use ATBS_P10_R3_3k_P7_NL. | 03/29/2022 6:58 AM | Dan Hazel | MFIA: Changed fixture as noted.
|  |  |  | 49 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | BUG Rating | Please include BUG Rating column. | 03/29/2022 6:58 AM | Dan Hazel | MFIA: Changed as noted.
|  |  |  | 50 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | LLF | Use 0.95 | 03/29/2022 6:58 AM | Dan Hazel | MFIA: Changed as noted.
|  |  |  | 51 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | Dimming | Please provide dimming column. Report as % full power. | 03/29/2022 6:58 AM | Dan Hazel | MFIA: Changed as noted.
|  |  |  | 52 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | Reference | Please reference CFA lighting plans provided to project team. Also see emails sent to Denise Taylor 2/18/2022. | 03/29/2022 6:58 AM | Dan Hazel
|  |  |  | 53 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | Calculations | Calculations shall be full width of roadway. Curb-to-curb analysis required. | 03/29/2022 6:58 AM | Dan Hazel | MFIA: Calc changed to include curb-to-curb.
|  |  |  | 54 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | Existing | Existing are ATBS P10 R3. Northern most corbahead fixture in front of Kaddy is a Leotek. IES file provided in Reviewer Documents folder. | 03/29/2022 6:58 AM | Dan Hazel | MFIA: Changes made as noted.
|  |  |  | 55 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | Zeros | Zeros shall not be removed if within ROW. | 03/29/2022 6:58 AM | Dan Hazel | MFIA: The note referring to 0's being masked is general and will be removed.
|  |  |  | 56 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | Avg | 70th Ave should have an avg of 0.4fc with a maximum of 0.52 and a uniformity of 6:1. Sidewalks shall have a minimum of 0.2fc with 10:1 uniformity. Target values for sidewalk are 0.4fc and 4:1 uniformity. | 03/29/2022 6:58 AM | Dan Hazel | MFIA: With the noted light levels, we are able to reduce to only one new street light to meet these levels.
|  |  |  | 57 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG TRAFFIC - DHAZEL | Connection | Connect to existing lighting controller south of Kaddy driveway. New lights shall be on separate cirucits. | 03/29/2022 6:58 AM | Dan Hazel | MFIA: Changes made as noted.
|  |  |  | 40 | False | Unresolved | ENG-Traffic Review |  | 016 PE1.04 Photometric Study.pdf | ENG_TRAFFIC - RICJO | Electrical Plan Sheet | Please upload a seperate sheet showing the electril plan including conduits(including the conduits in the PUE), junction boxes, wire sizes, etc. | 03/28/2022 3:24 PM | Jose Rico | MFIA: Changes made as noted. Contractor shall verify j-box, conduit and wire size with the city engineer prior to installation.